## Timesheet
Date | Activity | Workstream | Work Done | Output / Deliverable | Status | Hours (Actual) | Reference / Source | Kelvin.ai Compressor POC — Timesheet
2026-10-05 | POC Review | Existing System | Reviewed the existing Kelvin.ai compressor QA POC and current tree-based supervised model trained on synthetic data. | Established current-state baseline for the compressor QC POC. | Completed |  | Internal project discussion | Updated through 15-Oct-2026. Actual hours remain blank unless recorded. Research and design entries do not imply model training or deployment.
2026-10-05 | Fault Definition | Problem Framing | Documented the initial target post-shipment / QC fault classes: air leak, inlet-valve leakage, and outlet-valve leakage. | Initial compressor fault taxonomy. | Completed |  | Internal project discussion
2026-10-05 | Business KPI Design | Business Value | Reframed the POC from ML accuracy alone to business outcomes: defect-escape reduction, QC/troubleshooting time, warranty exposure, field-service effort, rework, and first-pass yield. | Business KPI framework. | Completed |  | Internal project discussion | Metric | Value
2026-10-05 | Dataset Research | Real Fault Data | Identified the IIT Kanpur real compressor acoustic dataset with healthy and multiple seeded fault classes including Leakage Inlet Valve, Leakage Outlet Valve, NRV, piston-ring, flywheel, rider-belt, and bearing faults. | Primary real-data candidate for fault-classification feasibility. | Completed |  | https://iitk.ac.in/iil/datasets/ | Logged Activities | 31
2026-10-05 | Dataset Research | Operational Sensor Data | Reviewed MetroPT-3 as a real operational compressor dataset with pressure/current/oil-temperature/control signals and documented air-leak periods. | Secondary candidate for real-world anomaly / leakage validation. | Completed |  | https://archive.ics.uci.edu/dataset/791/metropt%2B3 | Project Days | 6
2026-10-05 | Validation Strategy | POC Methodology | Clarified that public real data can validate the fault-detection approach for the POC; exact external validation of the current synthetic-trained model requires compatible input features. | Technically defensible validation statement for client presentation. | Completed |  | Internal project discussion | Completed | 31
2026-10-05 | Architecture Design | Plug-and-Play | Defined a two-stage plug-and-play concept: Stage 1 learns healthy behavior and flags unseen abnormal behavior; Stage 2 has a technician/compressor engineer verify the anomaly and assign the confirmed fault label. | Core healthy-only anomaly + human-labeling architecture. | Completed |  | Internal project discussion | Actual Hours Entered | 0
2026-10-05 | Continual Learning | Fault Library | Designed the feedback loop for storing confirmed anomalies, technician labels, false alarms, and recurring fault signatures so the system improves with customer-specific data. | Growing fault-signature / labeled incident library. | Completed |  | Internal project discussion
2026-10-05 | Fault Identification | Known vs Unknown | Defined three output levels: Normal/Abnormal, Known/Novel anomaly, and known fault classification; retained an UNKNOWN path so novel faults are not forced into an incorrect known class. | Safer fault-identification logic. | Completed |  | Internal project discussion
2026-10-05 | Sensor-Agnostic Design | Feature Engineering | Outlined modular feature groups for available sensors such as pressure, temperature, current, flow, vibration, and acoustic signals rather than hard-coding one sensor set. | Sensor-flexible feature architecture. | Completed |  | Internal project discussion
2026-10-05 | Operating-State Design | False Alarm Control | Identified the need to compare data within operating modes such as startup, unloaded, loaded, steady-state, and shutdown to avoid treating normal state transitions as anomalies. | Operating-state-aware anomaly detection requirement. | Completed |  | Internal project discussion
2026-10-06 | Model Concept Refinement | Expected vs Actual | Refined the QC concept around expected healthy behavior and residuals: model expected signal behavior under operating conditions and flag deviations while separating environment/installation effects from machine abnormality. | Residual-based health / anomaly concept. | Completed |  | Internal project discussion
2026-10-06 | Validation Requirements | Operating Envelope | Established that healthy training/validation should cover varied operating conditions so changes in load, environment, installation, or compressor state are not mistaken for faults. | Operating-envelope requirement for robust deployment. | Completed |  | Internal project discussion
2026-10-08 | Dataset Research | Healthy Baseline | Extended public-data research and identified RCSD-1YD, a one-year refinery centrifugal-compressor sensor dataset dominated by stable/normal operation, as a useful healthy-baseline candidate. | Additional healthy-operation dataset candidate. | Completed |  | https://ieeexplore.ieee.org/document/11006410/
2026-10-08 | Dataset Research | Anomaly / Failure Data | Identified MetroPT2 as a large real multivariate compressor time-series dataset with documented air-leak and oil-leak failure intervals; prioritized it for healthy-only anomaly experiments. | Large real operational anomaly-validation candidate. | Completed |  | https://zenodo.org/records/7766691
2026-10-08 | Data Availability Review | Deployment Planning | Noted that detailed public failure datasets are scarce and that production deployment will ultimately require customer/OEM historian, PLC/DCS, QC, maintenance, or service data for site-specific calibration and labels. | Data acquisition direction for real deployment. | Completed |  | Internal project discussion
2026-10-08 | POC Strategy | Plug-and-Play | Consolidated the POC flow: healthy baseline model → anomaly detection → technician verification → confirmed label → growing fault knowledge base; avoided claiming universal cross-compressor fault generalization. | Practical deployment and learning loop. | Completed |  | Internal project discussion
2026-10-08 | OEM Technology Research | Controls and Connectivity | Reviewed public OEM and practitioner accounts for Atlas Copco controllers, Gateway 4.0, SMARTLINK, and Burckhardt PROGNOST monitoring. Distinguished employee project descriptions from reposts. | Documented compressor integration options and supporting public references. | Completed |  | LinkedIn and OEM research in this chat
2026-10-08 | Manufacturing QC Research | Factory and Site Acceptance | Documented material inspection, assembly checks, pressure tests, controls FAT, mechanical running tests, performance testing, shipment inspection and SAT. | Twenty-stage compressor QC workflow and compressor-type comparison. | Completed |  | API guides and public FAT accounts in this chat
2026-10-08 | Documentation | QC Guide | Created a Word guide covering manufacturing QC, published FAT examples, required records and ML opportunities. Structural checks passed; visual rendering was unavailable. | Compressor_Manufacturing_Quality_Control_Guide.docx | Completed |  | Project root document
2026-10-13 | QC Scope Definition | Factory to Site Validation | Clarified the proposed QC scope around FAT-to-SAT deviations, installed performance and early quality issues; discussed limits of vibration-only diagnosis. | Proposed QC categories and factory-to-site comparison workflow. | Completed |  | Discussion in this chat; design only
2026-10-13 | Sensor Requirements | POC Design | Proposed process inputs covering pressure, flow, power, temperature, speed, operating state, lubrication and vibration. Identified limits on component-level diagnosis. | Candidate sensor list for a narrow QC POC. | Completed |  | Discussion in this chat; sensor availability not confirmed
2026-10-13 | Kelvin Integration Research | Platform Compatibility | Verified documented OPC UA and Modbus connections, Python applications, edge processing, asset dashboards, Data Explorer and recommendation views. | Proposed read-only Kelvin integration and built-in visualization approach; no deployment performed. | Completed |  | https://docs.kelvin.ai/latest/platform-administration/quick-start/connect-to-data/
2026-10-13 | RGC Workbook Inspection | BPCL Data Preparation | Inspected 2020_RGC.xlsx and identified RGC_A and RGC_B, a timestamp column and 71 tagged measurements for Compressor A. | Compressor A schema inventory and tag interpretation. | Completed |  | 2020_RGC.xlsx; supplied workbook
2026-10-13 | RGC Column Mapping | BPCL Data Preparation | Renamed tags by measurement category, extracted only RGC_A, and numbered columns by sensor type. Verified that measurement data were unchanged. | 2020_RGC_A_Sequential_Sensor_Names.xlsx and RGC_A_Sequential_Tag_Mapping.csv | Completed |  | outputs/rgc_compressor1/
2026-10-13 | Tag Interpretation Review | Sensor Semantics | Explained that CCRNIIK001AM1.PV may indicate motor current with K001A as equipment ID. Kept the interpretation unconfirmed pending the plant tag dictionary. | Documented motor-current hypothesis; no confirmed location or units. | Completed |  | Discussion in this chat; no subsequent workbook rename
2026-10-14 | Fault-Signature Review | Reciprocating Compressor | Reviewed likely reciprocating-compressor fault evidence for suction/discharge valve leakage, piston-ring wear, and cylinder faults using combinations of acoustic, vibration, cylinder pressure, crank-angle, and temperature information. | Fault-to-sensor evidence map concept. | Completed |  | Internal project discussion
2026-10-14 | Architecture Design | Multi-Asset / Edge | Refined a plug-and-play multi-asset flow using synchronized process/vibration/acoustic telemetry, operating-mode detection, a healthy-behavior model, fault-specific evidence, persistence checks, and maintenance advisory outputs. | Expanded deployment architecture. | Completed |  | Internal project discussion
2026-10-14 | Leak Detection Research | Acoustic / Ultrasonic | Reviewed handheld ultrasonic leak-detection practice and explored an Edge-AI concept using ultrasonic/acoustic features such as FFT/STFT to distinguish leak signatures from surrounding machinery noise. | Additional air-leak detection POC direction. | Completed |  | Internal project discussion
2026-10-15 | ML Results Audit | Project Status | Checked notebooks, reports and saved outputs. Confirmed that RGC preparation is complete but no RGC EDA, trained model, predictions or evaluation metrics are saved in this workspace. | Verified RGC implementation status; existing IITK EDA is separate. | Completed |  | Workspace file audit; notebooks/README.md; reports/eda/summary.json
2026-10-15 | Timesheet Update | Project Documentation | Added dated completed research, QC documentation, Kelvin feasibility review, RGC preparation and results-audit activities; retained prior records and left actual hours editable. | Updated project timesheet and date summary. | Completed |  | This workbook

## Summary
Kelvin.ai Compressor POC — Work Summary
Completed research and QC design, Kelvin integration feasibility, QC guide and RGC Compressor A preparation. RGC ML training and evaluation have not yet been performed in this workspace.
KPI | Value
Total logged activities | 31
Distinct work dates | 6
Completed activities | 31
Actual hours entered | 0
Date | Activities Logged | Key Milestone
2026-10-05 | 11 | Existing entries retained: synthetic-model review, business KPIs, dataset research and anomaly architecture.
2026-10-06 | 2 | Existing entries retained: expected-versus-actual concept and operating-envelope requirements.
2026-10-08 | 7 | Dataset and OEM research; manufacturing QC workflow; Word QC guide created.
2026-10-13 | 6 | QC scope and sensor requirements; Kelvin interface/dashboard research; RGC_A extraction and sequential sensor mapping.
2026-10-14 | 3 | Existing entries retained: reciprocating fault signatures, multi-asset concept and ultrasonic leak-detection research.
2026-10-15 | 2 | Audited saved ML work: no RGC model or results yet; updated timesheet.